## Client
Sprint ID | Priority | What
1 | 1 | CRUD info diri
1 | 1 | View packages
1 | 1 | Buy packages – default price not necessarily being used
| 4 | View purchased packages info – incl usage
| 2 | Create training request
| 3 | Request for cancellation

## Trainer
Sprint ID | Priority | What
1 | 1 | RU info diri
1 | 1 | View paket client di studio
1 | 1 | Set jam kerja per bulan
| 2 | Response training request
| 3 | View monthly report – jam kerja
| 2 | Konfirmasi latihan selesai
| 1 | Merubah harga paket ketika transaksi paket dengan client
| 1 | Melakukan penjualan paket

## Admin
Sprint ID | Priority | What
1 | 1 | CRUD paket
1 | 1 | CRUD karyawan dan status
| 2 | View total karyawan
| 2 | View total client – per status (trial /paying)
| 2 | View total paket terbeli
| 2 | View status paket – packages usage (leftover)
| 2 | View trainers working hour
| 3 | View studio’s calendar
| 3 | CRUD studios’ schedule
| 4 | View earning

## Jurnal
| Attendee |  |  |  | todo (D+1)
2019-10-08 | Z, A, J | WA con call | 1 | Introduction to PIS | 1 | Ali | Dummy authentication
[5 empty] | 2 | JT | Buat repo Github untuk EMDP
[5 empty] | 3 | Zul | Draft interface Login dan Admin (CRUD)